## техн (hidden)
Производство работ командированием рабочих
Вахтовый метод производства работ без организации вахтового городка (подтверждается предоставлением кол.договора)

## TCP with signature
Appendix 1
to Terms of Reference for Design and Survey, Construction and Assembly Works (CAW), Commissioning Works (SCW)
for Construction of Air Separation Block (ASB)
at Nevinnomyssk Azot JSC
Facility: Construction of Air Separation Block
Bidder __________________________________
The Cost of Quotation
Work Breakdown Structure (WBS) Item |  |  | Design (set of drawings) / Type of general design costs |  | Work Stages/Substages |  |  |  |  | Total cost, RUB | including
|  |  | Code | Description | Work Stage/Substage Code | Work Stage/Substage Description | Work Stage/Substage Result | UoM | Q-ty |  | CAW/ SCW/ Services | Equipment
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
[5 empty] | ПД-ЭР1 | Design stage | The results of the Complex Engineering Surveys, Design and Working Documentation were provided to and accepted by the Customer, a positive opinion of the State Expert Review of Design Documentation and Engineering Survey Results was provided. Designer's Supervision Service was provided |  |  | 125 | 125 | 0
15.99 | Customer's General Project Costs | [8 empty] | 125 | 125 | 0
| 15.99.01 Engineering, Contractor and Consulting Services | [8 empty] | 125 | 125 | 0
|  | 15.99.01.010 Survey Work (incl. Geodetic Survey) | [7 empty] | 15 | 15 | 0
|  |  | 15.99.01.010-ИИ | Complex engineering survey and inspection of existing buildings and structures, network sections. | [5 empty] | 15 | 15 | 0
[5 empty] | 15.99.01.010-ИИ-ПЭР1 | Complex engineering survey and inspection of existing buildings and structures, network sections. | Reports generated and verified by the Client on the results of engineering surveys and inspections of existing buildings and structures | set | 1 | 15 | 15 | 0
|  | 15.99.01.040 Engineering work: PD/FEED | [7 empty] | 20 | 20 | 0
|  |  | 15.99.01.040-ПД | Design documentation | [5 empty] | 20 | 20 | 0
[5 empty] | 15.99.01.040-ПД-ПЭР1 | Design documentation | Design documentation developed and verified by the Customer | set | 1 | 20 | 20 | 0
|  | 15.99.01.050 Engineering work: WD | [7 empty] | 15 | 15 | 0
|  |  | 15.99.01.050-РД | Working documentation | [5 empty] | 15 | 15 | 0
[5 empty] | 15.99.01.050-РД-ПЭР1 | Working documentation | Design documentation developed by Contractor and verified by the Customer | set | 1 | 15 | 15 | 0
|  | 15.99.01.060 Expert Review, Expert Support | [7 empty] | 20 | 20 | 0
|  |  | 15.99.01.060-ЭПД | Design Documentation Expert Review | [5 empty] | 20 | 20 | 0
[5 empty] | 15.99.01.060-ЭПД-ПЭР1 | Expert Review and Expert Support of Design Documentation and Engineering Surveys | Obtained Positive Opinion of the State Expert Review of Design Documentation and Engineering Survey results | set | 1 | 20 | 20 | 0
|  | 15.99.01.100 Designer's Supervision | [7 empty] | 55 | 55 | 0
|  |  | 15.99.01.100-АН | Construction Supervision Service | [5 empty] | 55 | 55 | 0
[5 empty] | 15.99.01.100-АН-ПЭР1 | Designer's Supervision Service for one quarter of Construction and Assembly Work | Designer's Supervision Service during the specified quarter was completed, the the log of Designer's Supervision was filled in, Acts of Concealed Works and Critical Structures in the specified period were signed | set | 1 | 10 | 10 | 0
[5 empty] | 15.99.01.100-АН-ПЭР2 | Designer's Supervision Service for one quarter of Construction and Assembly Work | Designer's Supervision Service during the specified quarter was completed, the the log of Designer's Supervision was filled in, Acts of Concealed Works and Critical Structures in the specified period were signed | set | 1 | 10 | 10 | 0
[5 empty] | 15.99.01.100-АН-ПЭР3 | Designer's Supervision Service for one quarter of Construction and Assembly Work | Designer's Supervision Service during the specified quarter was completed, the the log of Designer's Supervision was filled in, Acts of Concealed Works and Critical Structures in the specified period were signed | set | 1 | 10 | 10 | 0
[5 empty] | 15.99.01.100-АН-ПЭР4 | Designer's Supervision Service for one quarter of Construction and Assembly Work | Designer's Supervision Service during the specified quarter was completed, the the log of Designer's Supervision was filled in, Acts of Concealed Works and Critical Structures in the specified period were signed | set | 1 | 10 | 10 | 0
[5 empty] | 15.99.01.100-АН-ПЭР5 | Designer's Supervision Service for subsequent periods of Construction and Assembly Work, up to obtaining of Statement of Compliance from the Rostechnadzor (RTN) | Designer's Supervision Service during the specified quarter was completed, the the log of Designer's Supervision for all period of CAW, SCW was filled in, Acts of Concealed Works and Critical Structures in the specified period were signed | set | 1 | 15 | 15 | 0
[5 empty] | СТР-ЭР1 | Construction stage | CAW, SCW have been completed, the Statement of Compliance of the Constructed Facility with the Design Documentation was obtained from Rostechnadzor and handed over to the Customer. The complete set of As-Built Documentation on the results of Construction and Assembly Works and Commissioning is accepted by the Customer without any comments. The Facility has been tested and the performance and product quality parameters provided for in the Terms of Reference have been confirmed. |  |  | 3259 | 1424 | 1835
08.03 | In-site infrastructure (excluding underground mine utility networks) | [8 empty] | 615 | 390 | 225
| 08.05.02 | Electrical power supply and lighting system (according to Customer's specifications) | [7 empty] | 445 | 275 | 170
|  | 08.03.02.010 Transformer Substation (existing one, dispatcher designation is "PS-66") | [7 empty] | 90 | 50 | 40
|  |  | 08.03.02.010-ЭП | Implementation of Activities (reconstruction of two 6 kV switchgear cubicles) to ensure the connection of PS-73 (ASB) | [5 empty] | 90 | 50 | 40
[5 empty] | 08.03.02.010-ЭП-ПЭР1 | Replacing of a 6 kV Circuit Breaker and a set of Relay Protection and Automation Equipment in the first cubicle of Switchgear 6 kV | CAW is completed in the amount of 100% of the WD, a Certificate of Readiness for Commissioning is signed | set | 1 | 35 | 15 | 20
[5 empty] | 08.03.02.010-ЭП-ПЭР2 | Replacing of a 6 kV Circuit Breaker and a set of Relay Protection and Automation Equipment in the second cubicle of Switchgear 6 kV | CAW is completed in the amount of 100% of the WD, a Certificate of Readiness for Commissioning is signed | set | 1 | 35 | 15 | 20
[5 empty] | 08.03.02.010-ЭП-ПЭР3 | Commissioning | Commissioning of two 6 kV cubicles is completed in accordance with the SCW program agreed with the Customer | set | 1 | 20 | 20 | 0
|  | 08.03.02.011 Transformer Substation (existing one, dispatcher designation is "PS-66") | [7 empty] | 90 | 50 | 40
|  |  | 08.03.02.011-ЭП | Implementation of Activities (reconstruction of two 6 kV switchgear cubicles) to ensure the connection of PS-73 (ASB) | [5 empty] | 90 | 50 | 40
[5 empty] | 08.03.02.011-ЭП-ПЭР1 | Replacing of a 6 kV Circuit Breaker and a set of Relay Protection and Automation Equipment in the first cubicle of Switchgear 6 kV | CAW is completed in the amount of 100% of the WD, a Certificate of Readiness for Commissioning is signed | set | 1 | 35 | 15 | 20
[5 empty] | 08.03.02.011-ЭП-ПЭР2 | Replacing of a 6 kV Circuit Breaker and a set of Relay Protection and Automation Equipment in the second cubicle of Switchgear 6 kV | CAW is completed in the amount of 100% of the WD, a Certificate of Readiness for Commissioning is signed | set | 1 | 35 | 15 | 20
[5 empty] | 08.03.02.011-ЭП-ПЭР3 | Commissioning | Commissioning of two 6 kV cubicles is completed in accordance with the SCW program agreed with the Customer | set | 1 | 20 | 20 | 0
|  | 08.03.02.012 Packaged Transformer Substation (KTP 2х (kVA) - 6/0.4 power supply of ASB (to be constructed, dispatch designation "PS-73") | [7 empty] | 90 | 40 | 50
|  |  | 08.03.02.012-КЖ | Foundation | [5 empty] | 15 | 15 | 0
[5 empty] | 08.03.02.012-КЖ-ПЭР1 | Construction of reinforced-concrete foundations and a pile cap under the KTP | CAW of foundation is completed in the amount of 100% of the WD, a Inspection of Critical Structures Certificate is signed | set | 1 | 15 | 15 | 0
|  |  | 08.03.02.012-ЭП | 2х (kVA)-6/0.4 Packaged Transformer Substation Equipment | [5 empty] | 75 | 25 | 50
[5 empty] | 08.03.02.012-ЭП-ПЭР1 | Installation of KTP | Installation of KTP is completed in the amount of 100% of the WD and DD, Certificate of Hand-Over for Commissioning is signed | set | 1 | 60 | 10 | 50
[5 empty] | 08.03.02.012-ЭП-ПЭР2 | KTP Commissioning | KTP Commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 15 | 15 | 0
|  | 08.03.02.013 Packaged Transformer Substation (KTP 2х (kVA) - 6/0.69 (if 0.69 kV class voltages are necessary for regeneration heaters) | [7 empty] | 80 | 40 | 40
|  |  | 08.03.02.013-КЖ | Foundation | [5 empty] | 15 | 15 | 0
[5 empty] | 08.03.02.013-КЖ-ПЭР1 | Construction of reinforced-concrete foundations and a pile cap under the KTP | CAW of foundation is completed in the amount of 100% of the WD, a Inspection of Critical Structures Certificate is signed | set | 1 | 15 | 15 | 0
|  |  | 08.03.02.013-ЭП | 2х (kVA)-6/0,69 Packaged Transformer Substation Equipment | [5 empty] | 65 | 25 | 40
[5 empty] | 08.03.02.013-ЭП-ПЭР1 | Installation of KTP | Installation of KTP is completed in the amount of 100% of the WD and DD, Certificate of Hand-Over for Commissioning is signed | set | 1 | 50 | 10 | 40
[5 empty] | 08.03.02.013-ЭП-ПЭР2 | KTP Commissioning | KTP Commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 15 | 15 | 0
|  | 08.03.02.030 In-site power transmission lines, cable lines | [7 empty] | 95 | 95 | 0
|  |  | 08.03.02.030-ЭС1 | 6 kV cable lines and control circuits cable lines (from PS-66 to PS-72, from PS72 to PS73 (ASB) | [5 empty] | 45 | 45 | 0
[5 empty] | 08.03.02.030-ЭС1-ПЭР1 | Reinstatement of cable structures and replacement of 6 kV cable from PS-66 to PS-72 | Installation of cable structures is completed, the existing 6 kV cable is dismantled and new cable is laid in the amount of 100% of the WD, Certificate of Hand-Over for Commissioning is signed | set | 1 | 30 | 30 | 0
[5 empty] | 08.03.02.030-ЭС1-ПЭР2 | Installation of cable structures, 6 kV cable and control circuits cable lines from PS72 to PS73 (ASB) | Installation of cable structures and cable are completed in the amount of 100% of the WD, Certificate of Hand-Over for Commissioning is signed | set | 1 | 10 | 10 | 0
[5 empty] | 08.03.02.030-ЭС1-ПЭР3 | Cable lines commissioning | FOC lines commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 5 | 5 | 0
|  |  | 08.03.02.030-ЭС2 | Cable lines (from PS-73 to ASB Input Switching and Distribution Board - ISDB) | [5 empty] | 15 | 15 | 0
[5 empty] | 08.03.02.030-ЭС2-ПЭР1 | Installation of cable structures and 0.4 kV cable | Installation of cable structures and cable are completed in the amount of 100% of the WD, Certificate of Hand-Over for Commissioning is signed | set | 1 | 10 | 10 | 0
[5 empty] | 08.03.02.030-ЭС2-ПЭР2 | Cable lines commissioning | FOC lines commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 5 | 5 | 0
|  |  | 08.03.02.030-ЭС3 | 6 kV cable lines (if 0.69 kV class voltages are necessary for regeneration heaters) (from PS-73 6 / 0.4 to an additional KTP 2x (kVA) - 6 / 0.69) | [5 empty] | 20 | 20 | 0
[5 empty] | 08.03.02.030-ЭС3-ПЭР1 | Installation of cable structures, 6 kV cable and control circuits cable lines from PS72 to PS73 (ASB) | Installation of cable structures and cable are completed in the amount of 100% of the WD, Certificate of Hand-Over for Commissioning is signed | set | 1 | 15 | 15 | 0
[5 empty] | 08.03.02.030-ЭС3-ПЭР2 | Cable lines commissioning | FOC lines commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 5 | 5 | 0
|  |  | 08.03.02.030-ЭС4 | 0.69 kV cable lines (if 0.69 kV class voltages are necessary for regeneration heaters) (from KTP - 6/0.69 to ISDB -0.69 kV as part of ASP) | [5 empty] | 15 | 15 | 0
[5 empty] | 08.03.02.030-ЭС4-ПЭР1 | Installation of cable structures and 0.69 kV cable | Installation of cable structures and cable are completed in the amount of 100% of the WD, Certificate of Hand-Over for Commissioning is signed | set | 1 | 10 | 10 | 0
[5 empty] | 08.03.02.030-ЭС4-ПЭР2 | Cable lines commissioning | FOC lines commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 5 | 5 | 0
| 08.05.07 | Low power networks (including communication systems, safety systems, automated process control system (APCS), integration into existing systems, etc.) | [7 empty] | 45 | 15 | 30
|  | 08.03.07.060 Other in-site low power networks (LAN, Access Monitoring and Control System - AMCS, etc.) | [7 empty] | 45 | 15 | 30
|  |  | 08.03.07.030-СС | Communication and alarm networks (from the connection point according to the Customer's specifications to the communication and alarm cabinet as part of the ASB) | [5 empty] | 45 | 15 | 30
[5 empty] | 08.03.07.030-СС-ПЭР1 | Installation of cable structures (cable support structures) and laying of communication and alarm cables (fiber optical communications lines - FOCL). Installation of the FOCL active telecommunications equipment at the point of connection to the customer's existing network | Installation of cable structures and cable are completed in the amount of 100% of the WD, Certificate of Hand-Over for Commissioning is signed | set | 1 | 40 | 10 | 30
[5 empty] | 08.03.07.030-СС-ПЭР2 | FOCL commissioning | FOC lines commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 5 | 5 | 0
| 08.05.08 | Interconnecting/interprocessing pipe racks (including utilities networks and process pipelines) | [7 empty] | 125 | 100 | 25
|  | 08.03.08.070 Interconnecting/interprocessing pipe racks with utilities networks and process pipelines | [7 empty] | 125 | 100 | 25
|  |  | 08.03.08.070-КЖ | Reinforced concrete structures (foundations of piperacks supports for recycling water supply pipelines, steam lines, etc.) | [5 empty] | 25 | 25 | 0
[5 empty] | 08.03.08.070-КЖ-ПЭР1 | Construction of reinforced concrete foundations for process pipe racks, KTP cable entries | CAW of foundation is completed in the amount of 100% of the WD, a Inspection of Critical Structures Certificate is signed | set | 1 | 15 | 15 | 0
[5 empty] | 08.03.08.070-КЖ-ПЭР2 | Construction of reinforced concrete foundations to reinforce of existing structures | Concrete and earth works are completed in the amount of 100% of the WD, a Inspection of Critical Structures Certificate is signed | set | 1 | 10 | 10 | 0
|  |  | 08.03.08.070-КМ | Steel Structures | [5 empty] | 35 | 35 | 0
[5 empty] | 08.03.08.070-КМ-ПЭР1 | Installation of steel structures for process pipelines, KTP cable entries | Steel structural work is completed in the amount of 100% of the WD, an Inspection of Critical Structures Certificate is signed | set | 1 | 20 | 20 | 0
[5 empty] | 08.03.08.070-КМ-ПЭР2 | Installation of steel structures for pipe racks (to reinforce of existing structures) | Steel structural work is completed in the amount of 100% of the WD, an Inspection of Critical Structures Certificate is signed | set | 1 | 15 | 15 | 0
|  |  | 08.03.08.070-НВ | External water supply. Recycling water supply pipelines | [5 empty] | 20 | 15 | 5
[5 empty] | 08.03.08.070-НВ-ПЭР1 | Installation of recycling water supply pipelines from tie-in point to the ASB equipment according to Customer's specification | Pipelines installation is completed in the amount of 100% of the WD, Hydraulic (Pneumatic) Tests were performed, an Inspection of Critical Structures Certificate is signed | set | 1 | 20 | 15 | 5
|  |  | 08.03.08.070-ВС | Air supply | [5 empty] | 25 | 15 | 10
[5 empty] | 08.03.08.070-ВС-ПЭР1 | Installation of moist air duct from tie-in point to the ASB according to Customer's specification | Air duct installation is completed in the amount of 100% of the WD, Pneumatic Tests were performed, an Inspection of Critical Structures Certificate is signed | set | 1 | 15 | 10 | 5
[5 empty] | 08.03.08.070-ВС-ПЭР2 | Installation of compressed, dry instrument air supply pipeline for the ASB start-up from tie-in point to the ASB according to Customer's specification | Pipeline installation is completed in the amount of 100% of the WD, Pneumatic Tests were performed, an Inspection of Critical Structures Certificate is signed | set | 1 | 10 | 5 | 5
|  |  | 08.03.08.070-ВС | Heat supply | [5 empty] | 10 | 5 | 5
[5 empty] | 08.03.08.070-ТС-ПЭР1 | Installation of steam and condensate pipelines | Pipelines installation is completed in the amount of 100% of the WD, Hydraulic (Pneumatic) Tests were performed, an Inspection of Critical Structures Certificate is signed | set | 1 | 10 | 5 | 5
|  |  | 08.03.08.070-ТК | Process utilities | [5 empty] | 10 | 5 | 5
[5 empty] | 08.03.08.070-ТК-ПЭР1 | Nitrogen and other utilities supply lines installation for ASB start-up | Pipelines installation is completed in the amount of 100% of the WD, Hydraulic (Pneumatic) Tests were performed, an Inspection of Critical Structures Certificate is signed | set | 1 | 10 | 5 | 5
11.06 | Non-core production facilities, auxiliary warehouses, administrative buildings | [8 empty] | 2644 | 1034 | 1610
| 11.06.01 | Non-core production facilities | [7 empty] | 2644 | 1034 | 1610
|  | 11.06.01.040 Air separation products generation (oxygen, nitrogen, argon, etc.) | [7 empty] | 2557 | 987 | 1570
|  |  | 11.06.01.040-ГП | Plot Plan | [5 empty] | 20 | 20 | 0
[5 empty] | 11.06.01.040-ГП-ПЭР1 | Vertical levelling, construction of driveways and sidewalks, landscaping | CAW is completed in the amount of 100% of the WD. | set | 1 | 20 | 20 | 0
|  |  | 11.06.01.040-КЖ | Reinforced concrete structures (foundations of buildings, equipment, platforms for equipment) | [5 empty] | 15 | 15 | 0
[5 empty] | 11.06.01.040-КЖ-ПЭР1 | Construction of reinforced concrete foundations for buildings, block-modules, structures, equipment | Concrete and earth works are completed in the amount of 100% of the WD, an Inspection of Critical Structures Certificate is signed | set | 1 | 15 | 15 | 0
|  |  | 11.06.01.040-КМ | Steel Structures | [5 empty] | 25 | 25 | 0
[5 empty] | 11.06.01.040-КМ-ПЭР1 | Installation of steel framework, equipment structures, fences, etc. | Steel structural work is completed in the amount of 100% of the WD, an Inspection of Critical Structures Certificate is signed | set | 1 | 25 | 25 | 0
|  |  | 11.06.01.040-АР | Architectural Solutions | [5 empty] | 106 | 106 | 0
[5 empty] | 11.06.01.040-АР-ПЭР1 | Building of the roof | CAW is completed in the amount of 100% of the WD, an Inspection of Critical Structures Certificate is signed | set | 1 | 25 | 25 | 0
[5 empty] | 11.06.01.040-АР-ПЭР2 | Construction of exterior walls, building perimeter walks, ramps, etc. | CAW is completed in the amount of 100% of the WD, an Inspection of Critical Structures Certificate is signed | set | 1 | 26 | 26 | 0
[5 empty] | 11.06.01.040-АР-ПЭР3 | Construction of floor | CAW is completed in the amount of 100% of the WD, an Inspection of Critical Structures Certificate is signed | set | 1 | 27 | 27 | 0
[5 empty] | 11.06.01.040-АР-ПЭР4 | Installation of gates, doors, windows | CAW is completed in the amount of 100% of the WD, an Inspection of Critical Structures Certificate is signed | set | 1 | 28 | 28 | 0
|  |  | 11.06.01.040-ТХ | Process Equipment | [5 empty] | 1890 | 600 | 1290
[5 empty] | 11.06.01.040-ТХ-ПЭР1 | Installation of Air Pre-Cooling System | CAW is completed in the amount of readiness from the inlet to outlet flanges of the system, an Inspection of Critical Structures Certificate is signed | set | 1 | 210 | 60 | 150
[5 empty] | 11.06.01.040-ТХ-ПЭР2 | Installation of air dehydration and purification system | CAW is completed in the amount of readiness from the inlet to outlet flanges of the system, an Inspection of Critical Structures Certificate is signed | set | 1 | 250 | 70 | 180
[5 empty] | 11.06.01.040-ТХ-ПЭР3 | Installation of a cold generation system (except for a Turbo Expander) | CAW is completed in the amount of readiness from the inlet to outlet flanges of the system, an Inspection of Critical Structures Certificate is signed | set | 1 | 400 | 100 | 300
[5 empty] | 11.06.01.040-ТХ-ПЭР4 | Installation of Turbo Expander 1 | CAW is completed in the amount of readiness from the inlet to outlet flanges of the system, an Inspection of Critical Structures Certificate is signed | set | 1 | 240 | 30 | 210
[5 empty] | 11.06.01.040-ТХ-ПЭР5 | Installation of Turbo Expander 2 (if specified in the design proposed at the Tender stage) | CAW is completed in the amount of readiness from the inlet to outlet flanges of the system, an Inspection of Critical Structures Certificate is signed | set | 1 | 240 | 30 | 210
[5 empty] | 11.06.01.040-ТХ-ПЭР6 | The cost of the Turbo Expander spare cartridge (if specified in the design with one Turbo Expander proposed at the Tender stage) | The cartridge was delivered to the Customer's warehouse, the Acceptance Certificate was signed in accordance with the form established by the Customer | set | 1 | 150 | 0 | 150
[5 empty] | 11.06.01.040-ТХ-ПЭР7 | Nitrogen storage tank to maintain the ASB operability during Turbo Expander repair (if specified in the design with one Turbo Expander proposed at the Tender stage) | CAW is completed in the amount of readiness from the inlet to outlet flanges of the system, an Inspection of Critical Structures Certificate is signed | set | 1 | 30 | 10 | 20
[5 empty] | 11.06.01.040-ТХ-ПЭР8 | Process pipelines Installation | CAW is completed in the amount of 100% of the WD, a Certificate of readiness for Commissioning is signed | set | 1 | 320 | 250 | 70
[5 empty] | 11.06.01.040-ТХ-ПЭР9 | Commissioning Work | Commissioning of process equipment is completed in accordance with the SCW program agreed with the Customer | set | 1 | 50 | 50 | 0
|  |  | 11.06.01.040-АТХ | Process solution automation (DCS/ESD/PLC systems) | [5 empty] | 290 | 110 | 180
[5 empty] | 11.06.01.040-АТХ-ПЭР1 | Installation of Instrumentation, cable laying, installation of automated process control system (APCS) cabinet | CAW is completed in the amount of 100% of the WD. | set | 1 | 260 | 80 | 180
[5 empty] | 11.06.01.040-АТХ-ПЭР2 | APCS Commissioning (DCS/ESD/PLC systems) | Commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 30 | 30 | 0
|  |  | 11.06.01.040-ПС | Fire alarm system (in accordance with the Customer's specification) | [5 empty] | 35 | 15 | 20
[5 empty] | 11.06.01.040-ПС-ПЭР1 | Installation of the Automatic Fire Alarm (AFA) System, installation of of the FOCL active telecommunications equipment for the transmission of fire alarms to the existing Customer’s network | CAW is completed in the amount of 100% of the WD. | set | 1 | 30 | 10 | 20
[5 empty] | 11.06.01.040-ПС-ПЭР2 | AFA Commissioning | Commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 5 | 5 | 0
|  |  | 11.06.01.040-ВК | Water Supply and Sewage | [5 empty] | 12 | 7 | 5
[5 empty] | 11.06.01.040-ВК-ПЭР1 | Installation of recycling water system from external network to equipment | Pipelines installation is completed in the amount of 100% of the WD, Hydraulic (Pneumatic) Tests were performed, an Inspection of Critical Structures Certificate is signed | set | 1 | 10 | 5 | 5
[5 empty] | 11.06.01.040-ВК-ПЭР2 | Recycling Water System Commissioning | Commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 2 | 2 | 0
|  |  | 11.06.01.040-ЭМ | Power Supply Equipment | [5 empty] | 40 | 20 | 20
[5 empty] | 11.06.01.040-ЭМ-ПЭР1 | Installation of power distribution cabinets and control cabinets, Installation of cable support structures, installation of cable products | CAW is completed in the amount of 100% of the WD. | set | 1 | 35 | 15 | 20
[5 empty] | 11.06.01.040-ЭМ-ПЭР2 | Power Supply Equipment Commissioning | Commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 5 | 5 | 0
|  |  | 11.06.01.040-ЭО | Electric Lighting | [5 empty] | 16 | 11 | 5
[5 empty] | 11.06.01.040-ЭО-ПЭР1 | Installation of Electric Lighting System | CAW is completed in the amount of 100% of the WD. | set | 1 | 15 | 10 | 5
[5 empty] | 11.06.01.040-ЭО-ПЭР2 | Electric Lighting System Commissioning | Commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 1 | 1 | 0
|  |  | 11.06.01.040-ОВ | Heating, ventilation and air-conditioning (HVAC) systems | [5 empty] | 45 | 20 | 25
[5 empty] | 11.06.01.040-ОВ-ПЭР1 | Installation of Heating and Ventilation Systems | CAW is completed in the amount of 100% of the WD. | set | 1 | 20 | 10 | 10
[5 empty] | 11.06.01.040-ОВ-ПЭР2 | Installation of Air-Conditioning System | CAW is completed in the amount of 100% of the WD. | set | 1 | 20 | 5 | 15
[5 empty] | 11.06.01.040-ОВ-ПЭР3 | Commissioning Work | Commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 5 | 5 | 0
|  |  | 11.06.01.040-ЭН | External Electric Lighting | [5 empty] | 16 | 11 | 5
[5 empty] | 11.06.01.040-ЭН-ПЭР1 | Installation of ASB Area External Electric Lighting | CAW is completed in the amount of 100% of the WD. | set | 1 | 15 | 10 | 5
[5 empty] | 11.06.01.040-ЭН-ПЭР2 | External Electric Lighting Commissioning | Commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 1 | 1 | 0
|  |  | 11.06.01.040-ВС | Air supply | [5 empty] | 20 | 10 | 10
[5 empty] | 11.06.01.040-ВС-ПЭР1 | Installation of moist air duct from external network to equipment | Air duct installation is completed in the amount of 100% of the WD, Pneumatic Tests were performed, an Inspection of Critical Structures Certificate is signed | set | 1 | 10 | 5 | 5
[5 empty] | 11.06.01.040-ВС-ПЭР2 | Installation of compressed air supply line to pneumatic distributor panels | Pipeline installation is completed in the amount of 100% of the WD, Pneumatic Tests were performed, an Inspection of Critical Structures Certificate is signed | set | 1 | 10 | 5 | 5
|  |  | 11.06.01.040-ВС | Heat supply | [5 empty] | 15 | 10 | 5
[5 empty] | 11.06.01.040-ТС-ПЭР1 | Installation of steam and condensate pipelines from external network to heater | Pipelines installation is completed in the amount of 100% of the WD, Hydraulic (Pneumatic) Tests were performed, an Inspection of Critical Structures Certificate is signed | set | 1 | 10 | 5 | 5
[5 empty] | 11.06.01.040-ТС-ПЭР2 | Recycling Water System Commissioning | Commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 5 | 5 | 0
|  |  | 11.06.01.040-СС | Public Address System | [5 empty] | 12 | 7 | 5
[5 empty] | 11.06.01.040-СС-ПЭР1 | Installation of Public Address System | CAW is completed in the amount of 100% of the WD. | set | 1 | 10 | 5 | 5
[5 empty] | 11.06.01.040-СС-ПЭР2 | Public Address System Commissioning | Commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 2 | 2 | 0
|  | 11.06.01.041 Air separation products storage and offloading facilities, including tanks; | [7 empty] | 87 | 47 | 40
|  |  | 11.06.01.041-КЖ | Reinforced concrete structures (foundations for pipeline supports) | [5 empty] | 5 | 5 | 0
[5 empty] | 11.06.01.041-КЖ-ПЭР1 | Construction of reinforced concrete foundations for pipeline supports, block-modules, structures, equipment | Concrete and earth works are completed in the amount of 100% of the WD, an Inspection of Critical Structures Certificate is signed | set | 1 | 5 | 5 | 0
|  |  | 11.06.01.041-КМ | Steel Structures | [5 empty] | 8 | 8 | 0
[5 empty] | 11.06.01.041-КМ-ПЭР1 | Installation of supporting metal structures for air separation product pipelines | Steel structural work is completed in the amount of 100% of the WD, an Inspection of Critical Structures Certificate is signed | set | 1 | 8 | 8 | 0
|  |  | 11.06.01.041-ТХ | Process Equipment | [5 empty] | 58 | 23 | 35
[5 empty] | 11.06.01.041-ТХ-ПЭР1 | Connection of ASB to existing pipelines of liquid oxygen, nitrogen, etc. at points according to Customer’s specification (upstream of the existing tank) | Pipelines installation is completed in the amount of 100% of the WD, Hydraulic (Pneumatic) Tests were performed, an Inspection of Critical Structures Certificate is signed | set | 1 | 10 | 5 | 5
[5 empty] | 11.06.01.041-ТХ-ПЭР2 | Installation of liquid argon storage system (including cryogenic tank 10m3) | Pipelines and tank installation is completed in the amount of 100% of the WD, Hydraulic (Pneumatic) Tests were performed, an Inspection of Critical Structures Certificate is signed | set | 1 | 28 | 8 | 20
[5 empty] | 11.06.01.041-ТХ-ПЭР3 | Installation of a system for the offloading of liquid argon to tanker trucks and gaseous argon to cylinders | Pipelines installation is completed in the amount of 100% of the WD, Hydraulic (Pneumatic) Tests were performed, an Inspection of Critical Structures Certificate is signed | set | 1 | 15 | 5 | 10
[5 empty] | 11.06.01.041-ТХ-ПЭР4 | Argon Storage and Offloading Facilities Commissioning | Commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 5 | 5 | 0
|  |  | 11.06.01.041-ЭН | External Electric Lighting | [5 empty] | 16 | 11 | 5
[5 empty] | 11.06.01.041-ЭН-ПЭР1 | Installation of Liquid and Gaseous Argon Storage and Offloading Facilities Area External Electric Lighting | CAW is completed in the amount of 100% of the WD. | set | 1 | 15 | 10 | 5
[5 empty] | 11.06.01.041-ЭН-ПЭР2 | External Electric Lighting Commissioning | Commissioning is completed in accordance with the SCW program agreed with the Customer | set | 1 | 1 | 1 | 0
TOTAL Cost of the TCP | [9 empty] | 3384 | 1549 | 1835
VAT | 20% | [8 empty] | 677 | 310 | 367
TOTAL incl. VAT | [9 empty] | 4061 | 1859 | 2202
|  |  | Contractor |  |  |  | Signatory
|  |  | (Name of company) |  | (signature) |  | (name)
(Stamp here)
The bidder does not fill in the cells in which the formula is specified
Cells to be filled in by the bidder